## Summary
AF onboarding and framework backlog: estimate summary
All figures are formulas over the Backlog sheet. Change Size, Priority or Status there and this sheet updates.
Team velocity (points per sprint) | 30 | Assumption: example velocity, replace with your team's actual figure.
By phase | Stories | Points | Points done | Sprints (at velocity)
0 - Framework refactor (CS) | 26 | 98 | 0 | 3.2667
1 - AF foundation (CSAF) | 13 | 34 | 0 | 1.1333
2 - AF web form | 10 | 30 | 0 | 1
3 - AF specializations | 15 | 50 | 0 | 1.6667
4 - Test and go-live | 8 | 29 | 0 | 0.96667
5 - Future: CSTR | 11 | 51 | 0 | 1.7
Total | 83 | 292 | 0 | 9.7333
By priority | Stories | Points | Points done | Sprints (at velocity)
P1 - Must | 59 | 205 | 0 | 6.8333
P2 - Should | 14 | 39 | 0 | 1.3
P3 - Could / Future | 10 | 48 | 0 | 1.6
Total | 83 | 292 | 0 | 9.7333
By intensity | Stories | Points | Points done | Sprints (at velocity)
High | 23 | 129 | 0 | 4.3
Medium | 36 | 111 | 0 | 3.7
Low | 24 | 52 | 0 | 1.7333
Total | 83 | 292 | 0 | 9.7333
By size | Stories | Points | Points done | Sprints (at velocity)
S | 27 | 54 | 0 | 1.8
M | 42 | 126 | 0 | 4.2
L | 14 | 112 | 0 | 3.7333
Total | 83 | 292 | 0 | 9.7333
By category | Stories | Points | Points done | Sprints (at velocity)
AI | 3 | 13 | 0 | 0.43333
AI / business rules | 2 | 16 | 0 | 0.53333
AI / email | 1 | 3 | 0 | 0.1
Analysis | 1 | 3 | 0 | 0.1
Architecture | 5 | 13 | 0 | 0.43333
Background processing | 2 | 6 | 0 | 0.2
Case processing | 6 | 21 | 0 | 0.7
Configuration | 4 | 9 | 0 | 0.3
Configuration / DCR | 2 | 5 | 0 | 0.16667
Correspondence | 2 | 6 | 0 | 0.2
Data governance | 1 | 3 | 0 | 0.1
Data migration | 1 | 3 | 0 | 0.1
Data model | 7 | 25 | 0 | 0.83333
Database | 1 | 3 | 0 | 0.1
DevOps | 4 | 11 | 0 | 0.36667
Document generation | 2 | 6 | 0 | 0.2
Governance | 2 | 4 | 0 | 0.13333
Integration | 1 | 2 | 0 | 0.066667
Integration / email | 6 | 19 | 0 | 0.63333
Refactoring | 4 | 26 | 0 | 0.86667
Release | 1 | 3 | 0 | 0.1
Reporting | 1 | 3 | 0 | 0.1
Routing | 2 | 4 | 0 | 0.13333
Security | 6 | 21 | 0 | 0.7
Security / SSO | 1 | 3 | 0 | 0.1
Testing | 8 | 38 | 0 | 1.2667
UI | 1 | 2 | 0 | 0.066667
UI / DX component | 4 | 15 | 0 | 0.5
UI / localization | 1 | 3 | 0 | 0.1
Validation | 1 | 3 | 0 | 0.1
Total | 83 | 292 | 0 | 9.7333
AF go-live scope (P1, phases 0-4) | Stories | Points |  | Sprints (at velocity)
P1 stories excluding future CSTR | 59 | 205 |  | 6.8333

## Legend
Legend and how to use this workbook
Edit only the blue cells and the backlog columns Size, Intensity, Priority, Status, Owner. Story points and the Summary sheet recalculate from them.
T-shirt size | Story points | Meaning
S | 2 | Small, well understood change in one layer; little regression impact | Points per size as given by you (S=2, M=3, L=8); change the blue cells to re-weight.
M | 3 | Moderate change, a few rules or instances; some design or testing effort
L | 8 | Large or cross-cutting change; refactoring, several layers, or heavy regression
Intensity |  | Meaning (technical risk and regression impact)
High |  | Touches framework or security/isolation; failure affects Trinity or data separation
Medium |  | Some design choices or cross-layer effects; contained regression
Low |  | Configuration or AF-only change with local impact
Priority |  | Meaning
P1 - Must |  | Needed for Adrian Flux go-live
P2 - Should |  | Important; can follow shortly after go-live or ship if capacity allows
P3 - Could / Future |  | Future state (CSTR framework separation) or only if AF needs it
Status |  | Meaning
Not started
In progress
Blocked
Done
Story IDs: F = Phase 0 framework refactor (CS), A = Phase 1 AF foundation (CSAF), W = Phase 2 AF web form (CSAFWebExt), S = Phase 3 AF specializations, T = Phase 4 test and go-live, R = Phase 5 future CSTR. Section numbers refer to the framework document.

## Backlog
ID | Phase | Category | Story title | Description / scope | Acceptance criteria | Layer / app | Doc section | Size | Story points | Intensity | Priority | Depends on | Status | Owner / notes
F-01 | 0 - Framework refactor (CS) | Analysis | Capability inventory and rule tagging | List every Trinity capability and its rules; tag each Framework / Extend / Specialize. | Inventory signed off; every rule in the FNOL flow tagged; extension point list agreed. | CS | 2, 13 | M | 3 | Medium | P1 - Must |  | Not started
F-02 | 0 - Framework refactor (CS) | Refactoring | Scan CS rulesets for coverholder literals | Search CS and CSWebExt for 'Trinity', TRI-, mailbox domains, class names, case type IDs, logos. | Report of all hits with owning rule; each hit mapped to a refactoring story. | CS | 2, 16 | S | 2 | Low | P1 - Must | F-01 | Not started
F-03 | 0 - Framework refactor (CS) | Configuration | Coverholder configuration data type | Create HCC-CS-Data-CoverholderConfig, table and D_CoverholderConfig (node, keyed by CoverholderCode); add TRI row. | Data page returns TRI row; refresh on table change; PegaUnit on lookup. | CS | 6 | M | 3 | Medium | P1 - Must | F-01 | Not started
F-04 | 0 - Framework refactor (CS) | Configuration / DCR | Application context data page | Create HCC-CS-Data-AppContext, D_CSAppContext (requestor) and LoadAppContext with Trinity values. | D_CSAppContext returns TRI and class names in CS context; documented as overridable per ruleset. | CS | 6 | M | 3 | Medium | P1 - Must | F-03 | Not started
F-05 | 0 - Framework refactor (CS) | Data model | CoverholderCode on cases | Add .CoverholderCode to HCC-CS-Work; set in pyDefault of HCC-CS-Work-FNOL; expose as column. | New Trinity cases carry TRI; column populated and indexed. | CS | 6 | S | 2 | Low | P1 - Must | F-03 | Not started
F-06 | 0 - Framework refactor (CS) | Data migration | Backfill CoverholderCode on existing cases | Backfill TRI on open and closed Trinity FNOL and triage cases. | All existing cases have TRI; reconciliation count matches; run log kept. | CS | 6, 16 | M | 3 | Medium | P1 - Must | F-05 | Not started
F-07 | 0 - Framework refactor (CS) | Configuration / DCR | GetCoverholderCode resolver | Shared rule: case .CoverholderCode first, else D_CSAppContext. | Unit tests for case, case-less and background contexts. | CS | 6 | S | 2 | Low | P1 - Must | F-04, F-05 | Not started
F-08 | 0 - Framework refactor (CS) | Refactoring | Replace hard-coded values with config lookups | Replace literal class names, email accounts, prefixes, patterns, mailboxes found in F-02. | Zero literal hits in re-scan (except Trinity _Ext defaults); Trinity regression green. | CS | 3, 6 | L | 8 | High | P1 - Must | F-02, F-07 | Not started
F-09 | 0 - Framework refactor (CS) | Case processing | Refactor NewDefaults into template + extensions | Split NewDefaults; create DuplicateCheckCriteria_Ext, IsDuplicate_Ext, OnDuplicateFound_Ext, NewDefaults_Ext with Trinity defaults. | Trinity duplicate outcomes identical on regression set; PegaUnit per _Ext. | CS | 10 | L | 8 | High | P1 - Must | F-01 | Not started
F-10 | 0 - Framework refactor (CS) | Case processing | Class-aware duplicate candidate data page | D_DuplicateCandidates runs the duplicate report in the case's own class. | Query hits only the case's table; response time within agreed limit. | CS | 10 | M | 3 | Medium | P1 - Must | F-09 | Not started
F-11 | 0 - Framework refactor (CS) | Correspondence | Refactor confirmation correspondence | Split shared and coverholder paragraphs; sender account from config; ConfirmationRecipients_Ext. | Trinity emails unchanged; account name not hard-coded. | CS | 11 | M | 3 | Medium | P1 - Must | F-03 | Not started
F-12 | 0 - Framework refactor (CS) | Document generation | Refactor claim summary PDF | Shared claim-details section; ClaimSummaryPDF override point; file name prefix and category from config. | Trinity PDF identical; file name built from config. | CS | 11 | M | 3 | Medium | P1 - Must | F-03 | Not started
F-13 | 0 - Framework refactor (CS) | AI | Refactor AI image analysis configuration | Move prompt and thresholds to config or ImageAnalysisPrompt_Ext; confirm QP context handling. | Trinity analysis results unchanged; no literal prompt in framework activity. | CS | 11, 14 | M | 3 | Medium | P1 - Must | F-03, F-26 | Not started
F-14 | 0 - Framework refactor (CS) | Integration / email | Refactor outbound validation email | Template, recipient and subject pattern from config / correspondence by class. | Trinity validation email unchanged; subject pattern matches listener parsing. | CS | 12 | S | 2 | Low | P1 - Must | F-03 | Not started
F-15 | 0 - Framework refactor (CS) | Integration / email | Modularize triage processing on Work-Channel-Triage-Email | Refactor CS-ruleset triage rules into template + ClassifyReply_Ext, ExtractReplyEntities_Ext, ProcessReplyAttachments_Ext, HandOverToFNOL_Ext, OnTriageException_Ext, ResolveCaseFromSubject_Ext. | Trinity replies classified, linked and parsed exactly as before; each _Ext documented. | CS | 6, 12 | L | 8 | High | P1 - Must | F-01, F-03 | Not started
F-16 | 0 - Framework refactor (CS) | Integration / email | Stamp coverholder on triage cases | SetTriageCoverholder at triage creation from D_CSAppContext; expose column on triage table. | Every new triage case has CoverholderCode; column usable in reports and access rules. | CS | 12 | S | 2 | Medium | P1 - Must | F-04 | Not started
F-17 | 0 - Framework refactor (CS) | AI / business rules | Refactor parsed-data mapping and validations | MapParsedPolicyData_Ext and ApplyPolicyValidations_Ext on HCC-CS-Work-FNOL with Trinity defaults. | Trinity review tabs show identical data and validation results. | CS | 12 | L | 8 | High | P1 - Must | F-15 | Not started
F-18 | 0 - Framework refactor (CS) | Routing | Routing extension points | RouteToClaimHandler_Ext and exception routing via config/decision table. | Trinity routing unchanged; queues not hard-coded. | CS | 13, 14 | S | 2 | Low | P1 - Must | F-03 | Not started
F-19 | 0 - Framework refactor (CS) | Case processing | Libra ID validation from config | ValidateLibraID_Ext using pattern from config. | Trinity Libra IDs validate as today; invalid formats rejected. | CS | 12 | S | 2 | Low | P2 - Should | F-03 | Not started
F-20 | 0 - Framework refactor (CS) | Data model | Parameterize LOV and data-table data pages | Add CoverholderCode parameter; class from config via pxRetrieveReportData. | Trinity dropdowns unchanged; separate cache per coverholder. | CS | 9 | M | 3 | Medium | P1 - Must | F-03 | Not started
F-21 | 0 - Framework refactor (CS) | UI / DX component | Make DX component configuration-driven | Remove hard-coded values; add D_WebFormBootstrap; caseTypeID, LOVs, branding from config/bundle. | Trinity form behaves identically; no literal case type or coverholder in component code. | CS / CSWebExt | 8 | L | 8 | High | P1 - Must | F-20 | Not started
F-22 | 0 - Framework refactor (CS) | UI / DX component | Move component to shared component ruleset | Publish the custom component into a shared CS component ruleset. | Single component version used by CSWebExt; old copy withdrawn. | CS | 4, 8 | S | 2 | Medium | P1 - Must | F-21 | Not started
F-23 | 0 - Framework refactor (CS) | DevOps | Bundle key-parity check | Pipeline script comparing keys across web app bundles. | Pipeline fails on missing keys. | DevOps | 8 | S | 2 | Low | P2 - Should |  | Not started
F-24 | 0 - Framework refactor (CS) | Governance | Extension point catalogue | Document each _Ext rule: purpose, inputs, outputs, default. | Catalogue published and linked from rule descriptions. | CS | 13 | S | 2 | Low | P2 - Should | F-09, F-15 | Not started
F-25 | 0 - Framework refactor (CS) | Testing | Trinity regression and CS framework release | Full Trinity regression after Phase 0; release CS version. | Regression results identical to baseline; CS version locked. | CS | 15, 16 | L | 8 | High | P1 - Must | F-08 to F-22 | Not started
F-26 | 0 - Framework refactor (CS) | Architecture | Background processing inventory | List QPs, job schedulers, agents, SLAs in FNOL flow and their access-group context. | Inventory with decision per item: separate AF instance or case-resolved. | CS | 14 | M | 3 | Medium | P1 - Must | F-01 | Not started
A-01 | 1 - AF foundation (CSAF) | Architecture | Create CSAF application | CSAF built on CS; rulesets CSAF, CSAFInt, CSAFData; case types list. | Application opens; only AF case types shown. | CSAF | 4 | S | 2 | Low | P1 - Must | F-25 | Not started
A-02 | 1 - AF foundation (CSAF) | Data model | AF class group and classes | HCC-CSAF-Work class group, HCC-CSAF-Work-FNOL with directed parent HCC-CS-Work-FNOL; table mappings. | Classes created; rule resolution shows CS rules inherited. | CSAF | 5 | M | 3 | Medium | P1 - Must | A-01 | Not started
A-03 | 1 - AF foundation (CSAF) | Database | AF database tables (DDL) | Case, history and index tables with columns matching CS exposed columns plus duplicate-check indexes. | DDL executed in all environments; column parity verified. | DBA | 5 | M | 3 | Medium | P1 - Must | A-02 | Not started
A-04 | 1 - AF foundation (CSAF) | Case processing | AF case type | Thin case type rule calling CS processes; work ID prefix; pyDefault sets AF. | AF case created with correct prefix and CoverholderCode AF. | CSAF | 10 | M | 3 | Medium | P1 - Must | A-02, A-03 | Not started
A-05 | 1 - AF foundation (CSAF) | Testing | Stage-list comparison test | Unit test comparing CS and AF case type stages. | Test fails when stages diverge unexpectedly. | CSAF | 10 | S | 2 | Low | P2 - Should | A-04 | Not started
A-06 | 1 - AF foundation (CSAF) | Configuration | AF config row and context override | AF row in config table; LoadAppContext override in CSAF ruleset. | D_CSAppContext returns AF in CSAF context. | CSAF | 6 | S | 2 | Low | P1 - Must | A-01, F-04 | Not started
A-07 | 1 - AF foundation (CSAF) | Data model | AF LOV data type | HCC-CSAF-Data-LOV, own table, AF-only properties, data load, added to app data types. | AF dropdowns load AF values via shared data pages. | CSAF | 9 | M | 3 | Medium | P1 - Must | A-02, F-20 | Not started
A-08 | 1 - AF foundation (CSAF) | Data model | Other AF data tables | Apply LOV pattern to other web form / validation tables. | Each table loads AF data through shared data pages. | CSAF | 9 | M | 3 | Medium | P2 - Should | A-07 | Not started
A-09 | 1 - AF foundation (CSAF) | Security | AF roles, AROs and access groups | Access roles depending on CS roles; AROs on HCC-CSAF-; access groups ClaimHandler, Supervisor, Background, Admin. | AF users access only AF cases; Trinity users cannot open AF cases. | CSAF | 7 | M | 3 | High | P1 - Must | A-02 | Not started
A-10 | 1 - AF foundation (CSAF) | Security | Triage case isolation by coverholder | Access When / access control policy on .CoverholderCode for Work-Channel-Triage-Email. | Each coverholder sees only its own triage cases in UI, search and reports. | CS / CSAF | 7 | M | 3 | High | P1 - Must | F-16, A-09 | Not started
A-11 | 1 - AF foundation (CSAF) | Routing | AF work groups and work queues | CSAF_FNOL_Review, CSAF_Exceptions etc.; routing override. | AF assignments land only in AF queues. | CSAF | 14 | S | 2 | Low | P1 - Must | A-09, F-18 | Not started
A-12 | 1 - AF foundation (CSAF) | Security / SSO | Okta group mapping for AF users | Okta group(s) mapped to CSAF access groups in the authentication service. | AF user logs in via Okta into CSAF portal with correct access group. | CS / CSAF | 7 | M | 3 | Medium | P1 - Must | A-09 | Not started
A-13 | 1 - AF foundation (CSAF) | Case processing | AF SLA settings | AF goals/deadlines via config or SLA overrides. | AF SLAs fire with AF durations. | CSAF | 14 | S | 2 | Low | P2 - Should | A-04 | Not started
W-01 | 2 - AF web form | Architecture | Create CSAFWebExt application | CSAFWebExt built on CSAF (not CS). | Guest requestor's stack shows CSAFWebExt > CSAF > CS. | CSAFWebExt | 4, 8 | S | 2 | Low | P1 - Must | A-01 | Not started
W-02 | 2 - AF web form | Security | AF guest operator and access group | AF Guest User with CSAFWebExt:Guest: create case, read web form data pages, upload only. | Guest cannot open, list or search any case. | CSAFWebExt | 7 | S | 2 | Medium | P1 - Must | W-01 | Not started
W-03 | 2 - AF web form | Security | AF OAuth client and CORS | OAuth 2.0 client registration for AF web form; CORS restricted to AF host. | DX calls from AF host succeed; other origins rejected. | CSAFWebExt | 7, 8 | S | 2 | Medium | P1 - Must | W-02 | Not started
W-04 | 2 - AF web form | UI / localization | AF localization bundle | Bundle in CSAFWebExt with same keys; AF labels, placeholders, errors, tooltips, regex. | All keys present (parity check green); AF wording shown. | CSAFWebExt | 8 | M | 3 | Low | P1 - Must | W-01, F-23 | Not started
W-05 | 2 - AF web form | Configuration | AF web form bootstrap values | Case type ID, enabled sections, upload limits, allowed file types for AF. | Component bootstraps AF values; creates HCC-CSAF-Work-FNOL. | CSAFWebExt | 8 | S | 2 | Low | P1 - Must | F-21, A-06 | Not started
W-06 | 2 - AF web form | UI / DX component | AF-only optional fields | Add AF-only fields as config-enabled optional fields in the shared component (only if AF needs them). | Fields hidden for Trinity, shown for AF. | CS | 8 | M | 3 | Medium | P2 - Should | F-21 | Not started
W-07 | 2 - AF web form | Validation | Server-side validation for AF submission | Edit-validate on HCC-CSAF-Work-FNOL using the same patterns as the bundle/config. | Invalid payloads rejected via DX API even when client checks are bypassed. | CSAF | 8 | M | 3 | Medium | P1 - Must | A-04 | Not started
W-08 | 2 - AF web form | Security | Anonymous channel hardening | CAPTCHA / rate limiting, upload type allow-list, size limit, malware scan, log masking. | Pen-test findings on the channel closed; uploads scanned before AI analysis. | CSAFWebExt | 7 | L | 8 | High | P1 - Must | W-03 | Not started
W-09 | 2 - AF web form | UI / DX component | Embed and brand on AF host page | Embed component with AF client ID; AF theme/logo via bundle or theme settings. | AF page renders AF branding end to end. | CSAFWebExt | 8 | S | 2 | Low | P1 - Must | W-03, W-04 | Not started
W-10 | 2 - AF web form | Testing | DX API contract tests | Automated create tests for both guests: class, prefix, coverholder, attachments. | Tests in pipeline; green for Trinity and AF. | DevOps | 15 | M | 3 | Medium | P1 - Must | W-05 | Not started
S-01 | 3 - AF specializations | Case processing | AF duplicate check rules | AF overrides of DuplicateCheckCriteria_Ext, IsDuplicate_Ext, OnDuplicateFound_Ext. | PegaUnit cases for AF rules; no duplicate details exposed to claimant. | CSAF | 10 | M | 3 | Medium | P1 - Must | F-09, A-04 | Not started
S-02 | 3 - AF specializations | Correspondence | AF confirmation emails | AF ClaimConfirmation templates and paragraphs; recipient rules. | AF claimant/policy holder receive AF-branded email from AF account. | CSAF | 11 | M | 3 | Low | P1 - Must | F-11, S-06 | Not started
S-03 | 3 - AF specializations | Document generation | AF claim summary PDF | AF branding section; embedded fonts/images as binary rules. | AF PDF attached with AF name pattern. | CSAF | 11 | M | 3 | Low | P1 - Must | F-12 | Not started
S-04 | 3 - AF specializations | AI | AF image analysis settings and DPIA | AF prompts/thresholds only if different; confirm privacy terms for AI processing. | DPIA approved; AF photos analysed with AF settings. | CSAF | 11 | S | 2 | Medium | P2 - Should | F-13 | Not started
S-05 | 3 - AF specializations | Integration / email | AF validation email | AF template, recipient mailbox, subject with AF ID pattern. | AF validation team receives request with parsable subject. | CSAF | 12 | S | 2 | Low | P1 - Must | F-14 | Not started
S-06 | 3 - AF specializations | Integration / email | AF email accounts | Inbound and outbound AF email accounts with modern auth; secrets in auth profile. | Accounts connect in all environments. | CSAF | 12 | S | 2 | Medium | P1 - Must |  | Not started
S-07 | 3 - AF specializations | Integration / email | AF email channel and listener | Email channel in CSAF; generated listener and service email; service package access group CSAF:Background. | AF reply creates triage case in CSAF context with CoverholderCode AF. | CSAF | 12 | M | 3 | High | P1 - Must | S-06, A-09, F-16 | Not started
S-08 | 3 - AF specializations | AI / email | AF triage extension overrides | Override triage _Ext rules in CSAF ruleset only where AF replies differ. | AF replies classified, linked and parsed; Trinity unaffected. | CSAF | 6, 12 | M | 3 | High | P1 - Must | F-15, S-07 | Not started
S-09 | 3 - AF specializations | AI | AF NLP / text analytics model | Separate AF model only if AF reply format differs materially. | Model accuracy on AF sample meets agreed threshold. | CSAF | 12 | L | 8 | High | P2 - Should | S-08 | Not started
S-10 | 3 - AF specializations | AI / business rules | AF parsed-data mapping and validations | AF overrides of MapParsedPolicyData_Ext and ApplyPolicyValidations_Ext. | AF review tabs show correct data and AF validation outcomes. | CSAF | 12 | L | 8 | High | P1 - Must | F-17, S-08 | Not started
S-11 | 3 - AF specializations | UI | AF review view overrides | View overrides only for AF-only fields. | AF-only fields visible on review tabs. | CSAF | 12 | S | 2 | Low | P2 - Should | S-10 | Not started
S-12 | 3 - AF specializations | Background processing | AF queue processors and job schedulers | AF instances with CSAF:Background, or verified case-resolved, per F-26. | AF background items use AF templates, accounts and rules. | CSAF | 14 | M | 3 | High | P1 - Must | F-26, A-09 | Not started
S-13 | 3 - AF specializations | Integration | AF Libra entity / book code | Capture and display AF entity code if Libra requires it. | Libra ID and entity stored on AF case. | CSAF | 12 | S | 2 | Low | P3 - Could / Future | F-19 | Not started
S-14 | 3 - AF specializations | Reporting | AF reports and extracts | AF report definitions; CoverholderCode in BIX / warehouse extracts. | AF MI available; extracts split by coverholder. | CSAF | 14 | M | 3 | Medium | P2 - Should | A-03 | Not started
S-15 | 3 - AF specializations | Data governance | AF search, retention and archiving | Search config for AF classes; archive/purge policies for AF case and triage. | Policies configured and tested in non-prod. | CSAF | 14 | M | 3 | Medium | P2 - Should | A-03 | Not started
T-01 | 4 - Test and go-live | Testing | AF end-to-end scenario suite | Submit, duplicate, emails, AI, validation reply, triage, Libra, resolve. | All AF scenarios pass in staging. | DevOps | 15 | L | 8 | High | P1 - Must | Phase 3 | Not started
T-02 | 4 - Test and go-live | Testing | Isolation and security test pack | Cross-coverholder access via UI, URL, DX API, search, reports, triage. | No cross-coverholder access possible. | DevOps | 15 | M | 3 | High | P1 - Must | A-09, A-10 | Not started
T-03 | 4 - Test and go-live | Testing | Background-context tests | Verify QPs, jobs and listener process AF items with AF rules. | Log assertions confirm AF context for every background step. | DevOps | 15 | M | 3 | High | P1 - Must | S-12 | Not started
T-04 | 4 - Test and go-live | Testing | Performance tests | DX create + duplicate check at peak AF volume; AI queue throughput. | Response times and throughput within agreed limits. | DevOps | 15 | M | 3 | Medium | P1 - Must | T-01 | Not started
T-05 | 4 - Test and go-live | Security | Security review of anonymous AF channel | Pen test of CSAFWebExt and DX endpoints. | No open high/critical findings. | Security | 7 | M | 3 | High | P1 - Must | W-08 | Not started
T-06 | 4 - Test and go-live | DevOps | Product rules and environment settings | Product rules CS_Framework, CSAF, CSAFWebExt; env-specific values outside product rules. | Clean import into a fresh environment. | DevOps | 15 | M | 3 | Medium | P1 - Must | Phase 3 | Not started
T-07 | 4 - Test and go-live | DevOps | Pipeline with dual regression | CS change triggers Trinity and AF regression; deploy order enforced. | Pipeline blocks CS merge without green dual regression. | DevOps | 15 | M | 3 | Medium | P1 - Must | W-10, T-01 | Not started
T-08 | 4 - Test and go-live | Release | Production deployment and hypercare | Deploy in order; smoke test both coverholders; hypercare. | Both coverholders live and stable for the hypercare period. | All | 16 | M | 3 | High | P1 - Must | T-01 to T-07 | Not started
R-01 | 5 - Future: CSTR | Architecture | Create CSTR application for Trinity | CSTR built on CS; repoint Trinity access groups, Okta mapping and web app built-on. | Trinity behaviour unchanged; users run in CSTR context. | CSTR | 18 | M | 3 | High | P3 - Could / Future | T-08 | Not started
R-02 | 5 - Future: CSTR | Configuration | Move Trinity config and neutral framework default | TRI config row and Trinity LoadAppContext to CSTR; CS default raises clear error. | Missing override fails fast in CSTEST; Trinity unchanged. | CSTR / CS | 18 | S | 2 | Medium | P3 - Could / Future | R-01 | Not started
R-03 | 5 - Future: CSTR | Refactoring | Move Trinity _Ext defaults to CSTR (per capability) | Save Trinity _Ext versions into CSTR ruleset; replace CS defaults with neutral ones. Split into one story per capability when planned. | Per capability: Trinity regression green; CS default neutral. | CSTR / CS | 18 | L | 8 | High | P3 - Could / Future | R-02 | Not started
R-04 | 5 - Future: CSTR | Background processing | Move Trinity channel and background context | Trinity email channel service package to CSTR:Background; Trinity QPs and jobs to CSTR access groups. | Trinity background items run in CSTR context. | CSTR | 18 | M | 3 | High | P3 - Could / Future | R-01 | Not started
R-05 | 5 - Future: CSTR | Architecture | Trinity web app on CSTR | Create CSTRWebExt or rebuild CSWebExt on CSTR with Trinity bundle, guest and OAuth client. | Trinity web form works unchanged from the new app. | CSTRWebExt | 18 | M | 3 | Medium | P3 - Could / Future | R-01 | Not started
R-06 | 5 - Future: CSTR | Refactoring | Rename Trinity-flavoured rules and properties | Generic rule names, repoint callers, withdraw old; property strategy without in-place renames. | No coverholder names in CS rule names; no broken references. | CS | 18 | L | 8 | Medium | P3 - Could / Future | R-03 | Not started
R-07 | 5 - Future: CSTR | Data model | Trinity LOV data class | HCC-CSTR-Data-LOV with own table; move Trinity values. | Trinity dropdowns served from CSTR class. | CSTR | 18 | M | 3 | Medium | P3 - Could / Future | R-01 | Not started
R-08 | 5 - Future: CSTR | Testing | CSTEST neutral test implementation | Test app on CS with neutral coverholder; framework scenario tests. | Framework scenarios pass without Trinity or AF rules. | CSTEST | 18 | L | 8 | Medium | P3 - Could / Future | R-02 | Not started
R-09 | 5 - Future: CSTR | Governance | Framework governance model | Versioning, change requests with impact assessment, design authority, extension contract and deprecation policy. | Process approved and published. | All | 18 | S | 2 | Low | P2 - Should |  | Not started
R-10 | 5 - Future: CSTR | DevOps | Automated framework checks | Pipeline checks: literal scan on CS, guardrail threshold, catalogue entry for new extension points. | Pipeline fails on violations. | DevOps | 18 | M | 3 | Low | P2 - Should | F-02 | Not started
R-11 | 5 - Future: CSTR | Data model | Optional: new Trinity case class | HCC-CSTR-Work-FNOL for new Trinity cases from cutover; keep TRI- prefix and sequence; drain plan. | New cases in new class; in-flight cases complete; reports span both. | CSTR | 18 | L | 8 | High | P3 - Could / Future | R-03 | Not started
|  |  | Total | [5 empty] | 292